|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Time | Tasks | Who | Notes |
| Mon 13th Feb – Fri 17th Feb | 10am – 6pm | PREP WEEKS | Calum  Jamie  Craig | Kit Prep:  Speakers  Cable  Band Mic  Cast Mics  Ikea for Batteries |
| Sat 18th Feb – Sun 19th Feb |  | DAY OFF |  |  |
| Mon 20th Feb |  | NO CALL |  |  |
| Tues 21st Feb – Fri 24th Feb |  |  | Calum  Jamie  Craig | -VCA Plot  -Arrange Mic Fittings  -Sound Effects  -  -Stage Plans, Cable Plans  -Build RF Racks  -Build Amp Racks  -Check Every Microphone, Headset and DI  -Label Up Headsets and Mic Packs  -Set Up Mic Table Area  -Set Up Sound 2 Boxes |
| Sat 25th Feb |  | DAY OFF |  |  |
| Sun 26th Feb |  | DAY OFF |  |  |
| Mon 27th Feb | 2pm – 6pm  6pm – 9pm | Hire Delivery  Venue Prep | Calum  Jamie  Craig  Allan | -Clean out Void  - Donald, Vladmir & Radio World Set Up  -Cable Runs in Dips |
| Tues 28th Feb | 9am – 9pm | Fit UP | Calum  Jamie  Craig  Allan | -Flown Foldback Speakers  -FOH Position  -Install Sound Network  - |
| Wed 1st Mar | 9am – 9pm | Fit UP | Calum  Jamie  Craig  Allan |  |
| Thurs 2nd Mar | 9am – 9pm | Fit UP | Calum  Jamie  Craig  Allan | -Use Lunches to test all Mics |
| Fri 3rd Mar | 9am – 5pm  6pm – 9pm | Fit UP  Sound Quiet Time | Calum  Jamie  Craig  Allan | System Tuning |
| Sat 4th Mar | 9am – 9pm | Fit UP | Calum  Jamie  Craig  Allan | -Pit Set Up  -Band Foldback  -Stage Boxes  -Band Mic & Stand Prep |
| Sun 5th Mar |  | DAY OFF |  |  |
| Mon 6th Mar | 6pm – 9pm | NO CALL | Calum  Jamie  Craig  Allan |  |
| Tues 7th Mar | 9am – 9pm | Venue Prep | Calum  Jamie  Craig  Allan |  |
| Wed 8th Mar | 9am – 9pm | Venue Prep | Calum  Jamie  Craig  Allan |  |
| Thurs 9th Mar | 9am – 5pm  6pm – 9pm | Venue Prep  Cast EQ Session and Mic Fittings | Calum  Jamie  Craig  Allan |  |
| Fri 10th Mar | 10am  2pm  6pm | Rehearsal Run  Rehearsal Run  Sitzprobe | Calum  Jamie  Craig  Allan | -RS2  -Renfrew Street |
| Sat 11th Mar | 9am – 10am  10am – 1pm  2pm – 6pm | Sitzprobe Set Up  Sitzprobe (Band only)  Sitzprobe (w/Cast) | Calum  Jamie  Craig  Allan | -Ath Theatre |
| Sun 12th Mar |  | DAY OFF |  |  |
| Mon 13th Mar | 6pm – 9pm | TBC | Calum  Jamie  Craig  Allan |  |
| Tues 14th Mar | 9am – 9pm | Tech Rehearsal (w/Band) | Calum  Jamie  Craig  Allan |  |
| Wed 15th Mar | 9am – 9pm | Tech Rehearsal | Calum  Jamie  Craig  Allan |  |
| Thurs 16th Mar | 9am – 9pm | Tech Rehearsal | Calum  Jamie  Craig  Allan |  |
| Fri 17th Mar | 9am – 9pm | Dress Rehearsal 1 and 2 | Calum  Jamie  Craig  Allan |  |
| Sat 18th Mar | 9am – 10pm | Dress Rehearsal 3 and Preview | Calum  Jamie  Craig  Allan |  |
| Sun 19th Mar |  | DAY OFF |  |  |
| Mon 20th Mar | 6pm – 9pm | TBC | Calum  Jamie  Craig  Allan |  |
| Tues 21st Mar | Showcall | Performance 1 | Calum  Jamie  Craig  Allan |  |
| Wed 22nd Mar | Showcall | Performance 2 and 3 | Calum  Jamie  Craig  Allan |  |
| Thurs 23rd Mar | Showcall | Performance 4 and 5 | Calum  Jamie  Craig  Allan |  |
| Fri 24th Mar | Showcall | Gala Performance | Calum  Jamie  Craig  Allan |  |
| Sat 25th Mar | 9am – 9pm | Get Out and Transfer | Calum  Jamie  Craig  Allan |  |
| Sun 26th Mar |  | TRAVEL DAY |  |  |
| Mon 27th Mar | 9am – 10pm | Fit Up | Calum  Jamie  Craig  Allan |  |
| Tues 28th Mar | 9am – 10pm | Fit Up | Calum  Jamie  Craig  Allan |  |
| Wed 29th Mar | 9am – 1pm  2pm – 6pm  7pm – 10pm | Fit Up  Cast EQ Session  Technical Rehearsal | Calum  Jamie  Craig  Allan |  |
| Thurs 30th Mar | 9am – 12pm  1pm – 5pm  Showcall | Band Session  Dress Rehearsal  Performance 7 | Calum  Jamie  Craig  Allan |  |
| Friday 31st Mar | Showcall | Performance 8 | Calum  Jamie  Craig  Allan |  |
| Sat 1st Apr | Showcall | Performance 9 and 10 | Calum  Jamie  Craig  Allan |  |
| Sun 2nd Apr |  | TRAVEL DAY |  |  |
| Mon 3rd Apr | 9am – 9pm | Returns | Calum  Jamie |  |
| Tues 4th Apr | 9am – 9pm | Returns | Calum  Jamie |  |