|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Time | Tasks | Who | Notes |
| Mon 13th Feb – Fri 17th Feb | 10am – 6pm | PREP WEEKS | CalumJamieCraig | Kit Prep:SpeakersCableBand MicCast MicsIkea for Batteries |
| Sat 18th Feb – Sun 19th Feb |  | DAY OFF |  |  |
| Mon 20th Feb |  | NO CALL |  |  |
| Tues 21st Feb – Fri 24th Feb  |  |  | CalumJamieCraig | -VCA Plot-Arrange Mic Fittings-Sound Effects--Stage Plans, Cable Plans-Build RF Racks-Build Amp Racks-Check Every Microphone, Headset and DI-Label Up Headsets and Mic Packs-Set Up Mic Table Area-Set Up Sound 2 Boxes |
| Sat 25th Feb |  | DAY OFF |  |  |
| Sun 26th Feb |  | DAY OFF |  |  |
| Mon 27th Feb | 2pm – 6pm6pm – 9pm | Hire DeliveryVenue Prep | CalumJamieCraig Allan | -Clean out Void- Donald, Vladmir & Radio World Set Up-Cable Runs in Dips |
| Tues 28th Feb | 9am – 9pm | Fit UP | CalumJamieCraigAllan | -Flown Foldback Speakers-FOH Position-Install Sound Network- |
| Wed 1st Mar | 9am – 9pm | Fit UP | CalumJamieCraigAllan |  |
| Thurs 2nd Mar | 9am – 9pm | Fit UP | CalumJamieCraigAllan | -Use Lunches to test all Mics |
| Fri 3rd Mar | 9am – 5pm6pm – 9pm | Fit UPSound Quiet Time | CalumJamieCraigAllan | System Tuning |
| Sat 4th Mar | 9am – 9pm | Fit UP | CalumJamieCraigAllan | -Pit Set Up-Band Foldback-Stage Boxes-Band Mic & Stand Prep |
| Sun 5th Mar |  | DAY OFF |  |  |
| Mon 6th Mar | 6pm – 9pm | NO CALL | CalumJamieCraigAllan |  |
| Tues 7th Mar | 9am – 9pm | Venue Prep | CalumJamieCraigAllan |  |
| Wed 8th Mar | 9am – 9pm | Venue Prep | CalumJamieCraigAllan |  |
| Thurs 9th Mar | 9am – 5pm6pm – 9pm | Venue PrepCast EQ Session and Mic Fittings | CalumJamieCraigAllan |  |
| Fri 10th Mar | 10am2pm6pm | Rehearsal RunRehearsal RunSitzprobe | CalumJamieCraigAllan | -RS2-Renfrew Street |
| Sat 11th Mar | 9am – 10am10am – 1pm2pm – 6pm | Sitzprobe Set UpSitzprobe (Band only)Sitzprobe (w/Cast) | CalumJamieCraigAllan | -Ath Theatre |
| Sun 12th Mar |  | DAY OFF |  |  |
| Mon 13th Mar | 6pm – 9pm | TBC | CalumJamieCraigAllan |  |
| Tues 14th Mar | 9am – 9pm | Tech Rehearsal (w/Band) | CalumJamieCraigAllan |  |
| Wed 15th Mar | 9am – 9pm | Tech Rehearsal | CalumJamieCraigAllan |  |
| Thurs 16th Mar | 9am – 9pm | Tech Rehearsal | CalumJamieCraigAllan |  |
| Fri 17th Mar | 9am – 9pm | Dress Rehearsal 1 and 2 | CalumJamieCraigAllan |  |
| Sat 18th Mar | 9am – 10pm | Dress Rehearsal 3 and Preview | CalumJamieCraigAllan |  |
| Sun 19th Mar |  | DAY OFF |  |  |
| Mon 20th Mar | 6pm – 9pm | TBC | CalumJamieCraigAllan |  |
| Tues 21st Mar | Showcall | Performance 1 | CalumJamieCraigAllan |  |
| Wed 22nd Mar | Showcall | Performance 2 and 3 | CalumJamieCraigAllan |  |
| Thurs 23rd Mar | Showcall | Performance 4 and 5 | CalumJamieCraigAllan |  |
| Fri 24th Mar | Showcall | Gala Performance | CalumJamieCraigAllan |  |
| Sat 25th Mar | 9am – 9pm | Get Out and Transfer | CalumJamieCraigAllan |  |
| Sun 26th Mar |  | TRAVEL DAY |  |  |
| Mon 27th Mar | 9am – 10pm | Fit Up | CalumJamieCraigAllan |  |
| Tues 28th Mar | 9am – 10pm | Fit Up | CalumJamieCraigAllan |  |
| Wed 29th Mar | 9am – 1pm2pm – 6pm7pm – 10pm | Fit UpCast EQ SessionTechnical Rehearsal | CalumJamieCraigAllan |  |
| Thurs 30th Mar | 9am – 12pm1pm – 5pm Showcall | Band SessionDress RehearsalPerformance 7 | CalumJamieCraigAllan |  |
| Friday 31st Mar | Showcall | Performance 8 | CalumJamieCraigAllan |  |
| Sat 1st Apr | Showcall | Performance 9 and 10 | CalumJamieCraigAllan |  |
| Sun 2nd Apr |  | TRAVEL DAY |  |  |
| Mon 3rd Apr | 9am – 9pm | Returns | CalumJamie |  |
| Tues 4th Apr | 9am – 9pm | Returns | CalumJamie |  |