## Contents Page
Performing: 31/01/2019
Venue: New Athenaeum Theatre
Manual Contents
Production Schedule
Construction Phase Plan
Method Statement
Risk Assessments and SSOW

## CPP
Construction Phase Plan
| Production: Inner Space Race |  |  | Venue: New Athenaeum Theatre
PLAN | Principal Contractor Details |  | The Royal Conservatoire of Scotland, 100 Renfrew Street
| Principal Designer Details |  | The Royal Conservatoire of Scotland, 100 Renfrew Street
| Client Details |  | The Royal Conservatoire of Scotland, 100 Renfrew Street
| Description of Work |  | Build and dismantle of in-house built set, and the rigging of lighting and sound equipment.
Key Dates
| Load in and fit-up |  | Tuesday 29th January, 2019
(start of construction phase)
| Lighting focus |  | Tuesday 29th January, 2019
(construction phase complete)
| Stage Rehearsals |  | Wednesday 30th January, 2019
| First Performance |  | Thursday 31st January, 2019
| Get Out |  | Friday 1st Febuary, 2019
(construction phase)
PEOPLE | Key members of the production team and their responsibilities during the construction phase |  | Contact/Details
| Production Manager |  | Ewan Sullivan
Co-ordination of project work
| Stage Supervisor |  | Darren Wilson
Supervison of rigging and erection of scenery on stage
| Lighting Supervisor |  | Louisa Craig
Supervison of rigging of lighting and effects equipment for the production
| Sound Supervisor |  | Conor Brown
Supervison of sound equipment for the production
| Stage Manager |  | Lea Meloe
Supervison of rehearsals and performances stage
ORGANISATION | How the work will be safely managed during the construction phase
|  | Key Arrangements |  | Key Staff
| 1 | Introduction of key venue technical staff and induction to venue rules, emergency arrangements and fire plan at beginning of get-in |  | Venue Technicians
| 2 | Welfare arrangements - description of toilets, shower and green room facilities available in the venue during the get-in and fit-up |  | Venue Technicians
| 3 | Project briefing for work to be carried out on stage during the get-in and fit-up |  | Stage Supervisor
| 4 | The daily register of staff working on site during the production is at the stage door |  | Stage Supervisor
| 5 | First Aid arrangements: Nominated first aiders and first aid points |  | Client Services at Main Reception Desk
| 6 | RCS staff cover rota to be completed and communicated |  | Stage Manager
|  | Key Safety Risks on this Production |  | Key Control Measures
| 1 | Manual handling during load-in and strike periods |  | Risk Assessment Attached
| 2 | Overhead work |  | Risk Assessment Attached
| 3 | Slips, trips, and falls |  | Risk Assessment Attached
| 4 | Use of access equipment |  | Risk Assessment Attached
| 5 | Operation of counterweight and automated flying systems |  | Risk Assessment Attached

## RA Matrix
RCS |  | Risk Assessment Guidance Notes
Hazard |  | Persons At Risk |  | Is The Risk Adequately Controlled | What Further Action Needed to Control Risk
(Something with the potential to cause harm) |  | (Someone at risk from the hazard) |  | (What are the existing controls) | (What more could reasonably be done)
Examples |  | Examples |  | Examples | Examples
Slippage / Tripping |  | Teaching Staff |  | Is there adequate information / training? | Prioritise for risks affecting large numbers or where serious harm may result
Fire (flammable substances) |  | Cleaners |  | Are there adequate systems / procedures? | Consider:
Moving Parts |  | Maintenance Personnel |  | Does it meet legal requirements? | - Remove hazard completely
Working at Height |  | Students |  | Does it meet Conservatoire Policy/Standards? | - Try less risky option
Vehicles |  | Contractors |  | Does it comply with industry standards? | - Prevent access to hazard, e.g. guarding
Electrical wiring |  | Visitors |  | Does it represent good practice? | - Reorganise work to reduce exposure
Noise |  | The Public |  | Have you reduced risk as far as possible? | - Issue personal protective clothing
Manual handling |  | Operators |  | Calculate overall risk for job is V.High / High / Medium / Low. | - Welfare facilities - Washing / First Aid
Fumes |  | Young/inexperienced |  | Are you doing all that is reasonably practicable? | - Administrative controls
Dust |  | Trainees |  | Can I eliminate the hazard? | You are entitled to take cost into account (i.e. reasonably practicable).
Chemicals |  | People Working Alone |  | If not, how can I control the risk? | Review with Management. Assign responsibility and timescales.
Ergonomic |  | The Disabled |  | Personal protective clothing should only be used when no other reasonable action exists
Ignore the Trivial |  | Expectant Mothers
Performer
Concentrate on significant hazards which could seriously harm |  | Risk Index (Ri)
Calculated by multiplying Consequence / Severity (C) of Hazard by Likelihood (L) of it occurring. Use a 5 x 5 scale.
| Likelihood |  | Consequence / Severity |  | L x C
| 5 A Certainty |  | 5 Death |  | Low Risk = 1 - 6
| 4 Very Likely |  | 4 Serious injury disablement |  | Medium Risk = 7 - 11
| 3 Likely |  | 3 Lost time injury/illness |  | High Risk = 12 – 19
| 2 Unlikely |  | 2 Requires First Aid |  | Very High Risk = 20 – 25
| 1 Remote |  | 1 No injury/Minor Injury
Consult: Colleagues, specialists / competent persons, Data Sheets, Manuals, Accident / ill health records, Manufacturer’s instructions
HAZARD INDEX MATRIX
5x5 Scale | LIKELIHOOD
|  | A Certainty | Very Likely | Likely | Unlikely | Remote
SEVERITY |  | 5 | 4 | 3 | 2 | 1
Death | 5 | 25 | 20 | 15 | 10 | 5
Serious injury disablement | 4 | 20 | 16 | 12 | 8 | 4
Lost time injury/ illness | 3 | 15 | 12 | 9 | 6 | 3
Requires First Aid | 2 | 10 | 8 | 6 | 4 | 2
No Injury/ Minor Injury | 1 | 5 | 4 | 3 | 2 | 1
As Low as Reasonably Possible (ALARP)
Preliminary Hazard Analysis (PHA) |  |  |  | 5 Steps to Risk Assessment
SEVERITY
1 | No Injury/ Minor Injury |  |  | 1. Identify the hazard.
2 | Requires First Aid |  |  | 2. Identify who may be harmed and how.
3 | Lost time injury/ Minor Injury |  |  | 3. Analyse the risks - likelihood and severity.
4 | Serious Injury/ Illness |  |  | ●Consider the frequency and number of persons.
5 | Death |  |  | ●Establish a risk rating (Liklelihood x severity).
| LIKELIHOOD |  |  | ●Evaluate the risk and decide wether the exisitng precautions
1 | Remote |  |  | ●Decide on measures for risk reduction.
2 | Unlikely |  |  | 4. Record significant findings.
3 | Likely |  |  | 5. Review
4 | Very Likely
5 | A Certainty

## Fit up and Strike
| Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITIES/TASKS |  |  |  | Tutor/Lecturer/Production Manager - Comments
Task/Activity/Area: | Persons At Risk: | Ref: Inner Space | Initial Assessment Date: 14/01/2019
Fit Up & Strike | Employees/ Students
Department: TSM | Risk Assessment WITHOUT Controls: VERY HIGH | Risk Assessment WITH Controls:LOW | Last Assessment Date:
Site/Location: New Atheneum Theatre | Assessor: Darren Wilson |  | Reviewed By:
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C) | Tutor/Lecturer/Production Manager - Comments
Slips, trips and falls | Injury ranging from cuts, scrapes and bruises to broken bones. | 3 x 3 (9) | The stage and dock area will remain in working light during all aspects of fit up and strike period. | 1 x 4 (4)
Safety footware- EN ISO 20345 and PPE must be worn by all perosns working on the fit up and strike.
The stage and surrounding areas will be kept as clear as practicle during fit up and strike and technicians will clean up as they go.
After each fit up session the venue will be cleared for the next sessions work.
Manual handling- moving hard masking from dock to stage | Injury ranging from bruises, strains, sprains and fractures to long term spinal issues. | 3 x 4 (12) | The hard maskers must be moved by two people, one person watching the path ahead whilst the opther watching the top of the hard masking | 1 x 4 (4)
Safety footware- EN ISO 20345 and PPE must be worn by all perosns.
All work will be completed in accordance with CPU009 Manual Handling Risk Assessment
Operation of Counterweight Flying Sets | Injury ranging from bruises, concussions and fractures to death. | 3 x 5 (15) | All work will be completed in accordance with CPU003 Counterweight Flying, CPU005 Loading CW Bars, and CPU006 Unloading CW Bars Risk Assessments and Safe Systems of Work | 1 x 5 (5)
Tools, Objects or Personnel Falling From Height | Injury ranging from cuts and bruises to concussions, fractures and death. | 3 x 5 (15) | Safety footware- EN ISO 20345 and PPE must be worn by all perosns working on the fit up and strike. | 1 x 5 (5)
All work will be completed in accordance with CPU001 Overhead Work, CPU002 Grid Work, CPU011 Working at Height, and CPU100 Use of Tallescopes Risk Assessments and Safe Systems of Work
Use of Power Tools | Injury ranging from cuts and bruises to electric shock and death | 3 x 5 (15) | Only those who have been trained and are competent in the use of the power tools will be allowed to do so. | 1 x 5 (5)
Power tools will be used only when sufficent light is available for the given task.
All work will be completed in accordance with each indivuidal tools Risk Assessment and Safe System of Work.
Safety footware- EN ISO 20345 and PPE must be worn by all perosns undertaking power tool work.
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:

## Maze Structure
| Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITIES/TASKS |  |  |  | Tutor/Lecturer/Production Manager - Comments
Task/Activity/Area: | Persons At Risk: | Ref: Innerspace | Initial Assessment Date: 10/01/2019
Maze Structure | Employees/Students
Department: TSM | Risk Assessment WITHOUT Controls: HIGH | Risk Assessment WITH Controls: LOW | Last Assessment Date:
Site/Location: New Athanaeum Theatre | Assessor: Darren Wilson |  | Reviewed By:
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C) | Tutor/Lecturer/Production Manager - Comments
Maze structure collapsing | Injury ranging from bruising and lasceraitons to broken bones | 4x3 (12) | Hard masking and equipment used to build the maze structure will have at least one point of contact with adjacent pieces and will be joined using L brackets and hinges. Where this is not possible Kee Clamp foot plates, boom bases and scaff will be used to act as supports for the maze wall pieces. All maze wall pieces will be secured at 5 or more places to prevent falling. | 1x3 (3)
Hard edges of maze structure | Bruising, lasceraitons | 3x3 (9) | All hard edges of maze structure will be covered over with excess masking cloth to avoid brusing and lasceraitons. | 1 x 3 (3)
Players will be shown a safety video or read a safety notice before entering the maze.
Players will be asked to wear suitable footwear whilst inside the maze.
Maze edges will be taped with white matt gaff so they are visable to palyers.
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:

## CPU001 Overhead RA
Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITIES/TASKS
Task/Activity/Area: Overhead Work | Persons At Risk: Employees/Visitors/Contractor/ Public/Students | Ref: CPU001 | Initial Assessment Date: 19/09/16
Department: Production | Risk Assessment WITHOUT Controls: HIGH | Risk Assessment WITH Controls: LOW | Last Assessment Date: 23/05/18
Site/Location: All RCS Venues, working spaces or touring venues. | Assessor: M. Stephen |  | Reviewed By: S.Macluskie
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C)
Falling Objects landing on persons below | Injury to any body part being struck causing injuries from bruising to death. | 3 x 5 (15) | An orange flashing light will be turned on to indicate that overhead work is taking place at which time Safety Helmets EN 397 and Safety Footwear EN ISO 20345 must then be worn. Personnel doing overhead work will remove all loose items. All tools to be kept on lanyards. All work to be carried out by trained personnel or under supervision by an appropriate staff member. If there is potential for there to be loose items to fall, the area under the work should be isolated until the work is complete. Stage access limited to only those working there at the time. | 1 x 5 (5)
Being struck by items being lifted or lowered | Injury to any body part being struck causing injuries from bruising to death. | 3 x 5 (15) | An orange flashing light will be turned on to indicate that overhead work is taking place at which time Safety Helmets EN 397 and Safety Footwear EN ISO 20345 must then be worn. Lifting/Lowering operations are called and watched by an appointed floor manager. All work to be carried out by trained personnel or under supervision by an appropriate staff member. If there is potential for there to be loose items to fall, the area under the work should be isolated until the work is complete. Stage access limited to only those working there at the time. Everyone will be made aware of lifting/lowering operations by clear vocalisation of the action. | 1 x 5 (5)
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:
Tensile barriers to cordon off stage areas |  | 2019-06-01 | Malcolm Stephen
Clear signage at Grid level about tools and loose items |  | 2018-10-01 | Malcolm Stephen
Permanent warning lights for CST and NAT Stalls |  | 2019-06-01 | Malcolm Stephen

## SSoW Overhead
RCS Production Safe Systems of Work
Overhead Work
Hazards | PPE Required
Falling objects. | Orange warning light
People being stuck by items being lifted or lowered. | Safety Helmet - EN 397
Tool lanyards
Safety Footwear - EN ISO 20345
Operational Procedure
Overhead work defined as any situation where personnel are at risk of being struck by items coming from above.
General
1. During overhead work in the theatre spaces an orange flashing light indicating overhead work must be switched on and everyone onstage made aware that the space has become a hard hat area.
2. Anyone working below the overhead work must also wear safety footwear.
Personnel undertaking overhead work
1. Personnel engaging in overhead work must secure tools on a lanyard.
2. Personnel engaging in overhead work must remove all loose items that have the potential to cause harm if they fall.
3. Personnel engaging in overhead work but still at risk from items coming from above must wear Safety Helmets - EN 397 with a chin strap.
Personnel working below any overhead work
1. When overhead work is about take place the orange light will flash. Safety Helmets must be put on at this point.
2. Safety Helmets - EN 397 must be kept on for the duration of the overhead work.
3. When the work is completed the light may be switched off if the designated floor manager or staff member deems it safe.
4. Only once the light is off and the floor manager or staff member has deemed it safe to do so, may Safety Helmets be removed.
When Finished
1. Those engaging in overhead work to return RCS tool lanyards to designated place.
2. Hard hats to be returned to their storage point.
Notes:
During focus sessions the orange flashing light may be kept off, but those immediately under the person focusing should still wear hard hats and safety footwear. The person focusing must also have all tools on lanyards.
Localised short duration work i.e. footing a ladder, or for work outside of the theatre spaces, hard hats may have to be worn and an assessment of the risk should be made to see if they are required. The orange warning light will not be required for every instance and personnel should follow this RA and SSoW to keep themselves safe from all iterations of overhead work.
It is forbidden for anyone under the influence of drugs, alcohol or reaction impairing medication to engage in work activities.

## CPU003 CW Flying RA
Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITIES/TASKS
Task/Activity/Area: | Persons At Risk: | Ref: CPU003 | Initial Assessment Date: 01/6/16
Counterweight Flying | Employees/Students
Department: Production | Risk Assessment WITHOUT Controls: HIGH | Risk Assessment WITH Controls: LOW | Last Assessment Date: 23/5/18
Site/Location: New Athenaeum Theatre | Assessor: M. Stephen |  | Reviewed By: Steve MacLuskie
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C)
People being stuck by flying bars or flown scenery. | Injury from ranging from bruises to severe concussions/fractures. | 4 x 4 (16) | Stage access limited to only those working there at the time. Everyone made aware of bars in motion with clear vocalisation. Bars are watched in by an appointed person who is in clear communication with the fly person. Orange flashing light to be switched on when flying outside of technical rehearsals and performance in accordance with 'Overhead Work' RA/SSoW and Safety Helmets EN 397 and Safety Footwear EN ISO 20345 must then be worn. Clearly marked deads will be applied to each bar that is in use to avoid overflying. Clear communication maintained between fly person and floor during flying. | 1 x 4 (4)
Fly operator being hit with cradle. | Head and upper body injuries | 3 x 3 (9) | Operators to be trained properly and made fully aware of the cradle travel. As far as is practical, head and arms to be kept out of the travel zone when the cradles are in motion. | 1 x 3 (3)
Falling items due to failure of equipment, accessories or load structure. | Injury from falling objects ranging from bruises to severe concussions/fractures and death. | 3 x 5 (15) | System is fully checked every 12 months by a qualified independent body. Flying accessories are checked every 6 months. Individual bars and terminations to be examined visually every time a load is to be attached to them. All faults are reported upon discovery and either resolved or the equipment taken out of use until it can be repaired. Orange flashing light to be switched on when flying outside of technical rehearsals and performance in accordance with 'Overhead Work' RA/SSoW and Safety Helmets EN 397 and Safety Footwear EN ISO 20345 must then be worn. | 1 x 5 (5)
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:

## SSoW CW Flying
RCS Production Safe Systems of Work
Flying Counterweight Bars
Hazards | PPE Required
Being struck by bars/scenery/cradles | Safety Helmet - EN 397
Equipment failure | Safety Footwear - EN ISO 20345
Operator being struck by moving cradle | Gloves (Optional - for comfort)
Operational Procedure
1. Before moving a bar, the bars travel must be checked to ensure it is clear.
2. An appointed floor manager must be present if the bar or load is to travel below fly floor level.
3. Once it is deemed safe a bar can be moved. Whilst keeping a firm grip of both ropes, or the front rope and the rope of an adjacent bar if the cradle is in the way, the brake may be slowly released to test that the load is in balance. If it is not, the brake should be applied along with a rope lock till the bar is weighted correctly.
4. The brake can then be released allowing the balanced bar to travel. A clear shout denoting the bar number and direction of travel should be given prior to the bar moving. E.g. If bar 2 is to be moved upwards, the operator would shout "Bar 2 going OUT". For a bar moving inwards it would be "Bar 2 coming IN". The travel of the bar should be watched at all times by the floor manager.
5. If a bar has a long way to travel till i.e. from the grid to stage level, then a second shout may be required as the bar passes the fly floor to ensure people are still aware of the bars movement.
6. During technical rehearsals and shows, bars should be spotted in by a floor manager where there is a danger of cast or crew being struck by flying items.
7. Once the bar has been moved to the desired position, the brake can be applied.
It is forbidden for anyone under the influence of drugs, alcohol or reaction impairing medication to engage in work activities.

## CPU004 Performance Flying RA
Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITIES/TASKS
Task/Activity/Area: | Persons At Risk: | Ref: CPU004 | Initial Assessment Date: 01/6/16
Flying in Performance | Employees/Students
Department: Production | Risk Assessment WITHOUT Controls: HIGH | Risk Assessment WITH Controls: LOW | Last Assessment Date: 23/5/18
Site/Location: New Athenaeum Theatre | Assessor: M. Stephen |  | Reviewed By: Steve MacLuskie
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C)
People being stuck by flown items. | Injury from ranging from bruises to severe concussions/fractures. | 4 x 4 (16) | Stage access limited to only those working there at the time. Clearly marked deads will be applied to each bar that is in use to avoid overflying. All actions rehearsed fully. Items flown close to cast or crew to be watched in by a floor manager or appointed spotter who is in direct communication with the fly-floor. Items only called in by floor manager or on cue by the DSM when it safe to do so. | 1 x 4 (4)
Fly operator being hit with cradle. | Head and upper body injuries | 3 x 3 (9) | Operators to be trained properly and made fully aware of the cradle travel. As far as is practical, head and arms to be kept out of the travel zone when the cradles are in motion. | 1 x 3 (3)
Falling items due to failure of equipment, accessories or load structure. | Injury from falling objects ranging from bruises to severe concussions/fractures and death. | 3 x 5 (15) | System is fully checked every 12 months by a qualified independent body. Flying accessories are checked every 6 months. Individual bars and terminations to be examined visually every time a load is to be attached to them. All faults are reported upon discovery and either resolved or the equipment taken out of use until it can be repaired. | 1 x 5 (5)
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:

## Flying Performance SSOW
RCS Production Safe Systems of Work
Flying counterweights for rehearsal and performance
Hazards | PPE Required
Being struck by a flying item | Gloves (Optional - for comfort of fly person)
Operator being struck by moving cradle
Equipment failure
Operational Procedure
Operations to be completed by trained personnel under controlled circumstances
Rehearsals:
All bars must be called in or out by a floor manager or the DSM and only when it is safe to do so.
All actions logged with bar number, speed and dead.
Difficult flying sequences to be rehearsed in full light till everyone is comfortable with the action.
Performance:
Each fly person is responsible for their own cue stack and must know what action is coming up next. All actions in the cue stack will be extensively rehearsed during the technical rehearsal period.
On a call to standby for a particular cue, the fly person will re-check with the running list what bar is moving, in what direction, to which dead and at what speed for that cue.
The fly person will then hold both the front and back ropes (or front and the rope of an adjacent line if the cradle is in the way)) firmly and release the brake.
On the Go for that cue, the fly person will complete the cue as rehearsed and brake the bar.
The fly person will then check their cue sheet to see what they next action is and prepare for it.
It is forbidden for anyone under the influence of drugs, alcohol or reaction impairing medication to engage in work activities.

## CPU005 Loading CW Bars RA
Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITIES/TASKS
Task/Activity/Area: | Persons At Risk: | Ref: CPU005 | Initial Assessment Date: 01/06/16
Loading Counterweight Bars | Employees/Students
Department: Production | Risk Assessment WITHOUT Controls: HIGH | Risk Assessment WITH Controls: LOW | Last Assessment Date: 23/5/18
Site/Location: New Athenaeum Theatre | Assessor: M. Stephen |  | Reviewed By: Steve MacLuskie
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C)
Manual handling fly weights | Bruises, strains, sprains and fractures | 3 x 4 (12) | All people handling fly weight will have undergone RCS Manual Handling Awareness training and cradle loading and unloading training. Cradles will be loaded by teams of two people wherever possible. Counterweights are loaded one at a time. Safety footwear EN ISO 20345 will be worn at all times. | 1 x 4 (4)
Manual handling. Moving scenery or lighting/sound equipment into position for rigging onto counterweight bar. | Bruises, strains, sprains and fractures | 3 x 4 (12) | All participating people must have attended RCS Manual Handling awareness training. The weight of all items should be known prior to moving them. An appropriate amount of people used to manoeuvre the item into position. Route of travel must be clear of all trip hazards. Clear communication must be maintained. Safety footwear EN ISO 20345 will be worn at all times. | 1 x 4 (4)
People being stuck by flying bars or flown scenery. | Injury from ranging from bruises to severe concussions/fractures. | 4 x 4 (16) | Stage access limited to only those working there at the time. Everyone made aware of bars in motion with clear vocalisation. Bars are watched in by an appointed person who is in clear communication with the fly person. Orange flashing light to be switched on when flying outside of technical rehearsals and performance in accordance with CPU 001 'Overhead Work' RA/SSoW and Safety Helmets EN 397 and Safety Footwear EN ISO 20345 must then be worn. Clearly marked deads will be applied to each bar that is in use to avoid overflying. Clear communication maintained between fly person and floor manager during flying. | 1 x 4 (4)
Falling fly weights from grid to stage level. | Injury ranging from bruises to severe concussions/fractures and death | 3 x 5 (15) | All people handling fly weights will have been trained in how to do so and be aware of the risks involved. While cradles are being loaded the area near the fly cages will be kept as free of people as possible by the floor manager. All 1/2 weights will be put in under a full fly weight to prevent half weight bouncing out of the cradle. Everyone at floor level will wear Safety Helmets - EN397 and Safety Footwear - EN ISO 20345 | 1 x 5 (5)
Runaway bars from incorrect loading. | Injury ranging from bruises to severe concussions/fractures and death | 3 x 5 (15) | Accurate weights of loads to be known prior to the commencement of the operation. Communication between Loading and Floor Manager will be done through the Head of Flys. All bars will be secured with a rope clip while loading and unloading takes place. Clear communication maintained throughout the operation. Everyone at floor level will wear Safety Helmets - EN397 and Safety Footwear - EN ISO 20345 | 1 x 5 (5)
Falling items due to failure of equipment, accessories or load structure. | Injury ranging from bruises to severe concussions/fractures and death | 3 x 5 (15) | System is fully checked every 12 months by a qualified independent body. Flying accessories are checked every 6 months. Individual bars and terminations to be examined visually every time a load is to be attached to them. All faults are reported upon discovery and either resolved or the equipment taken out of use until it can be repaired. Scenic items are built to a suitable standard rigged in a way appropriate to their structure and mass. Everyone at floor level will wear Safety Helmets - EN397 and Safety Footwear - EN ISO 20345 | 1 x 5 (5)
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:

## SSoW Counterweight Loading
RCS Production Safe Systems of Work
Loading Counterweight Bars
Hazards | PPE Required
Being struck by flying bars or scenery | Safety Helmet - EN 397
Falling weights from loading gallery | Safety Footwear - EN ISO 20345
Incorrect manual handling of weights or loads | Gloves (Optional - for comfort of fly person)
Runaway bars | Rope Clip
Falling loads
Operational Procedure
An approved member of staff must be present in the venue
Personnel must include: Floor manager, fly person on fly floor, 2 persons on loading gallery.
1. The orange flashing light to denote 'overhead work' must be switched on. All ground personnel must then wear hard hats.
2. Floor manager will instruct the fly person to bring in the required bar when it is safe to do so and the fly person will fly it until it is fully in and so the cradle is against the buffers at the top of the system
3. When the bar is fully in, the fly person will apply the brake and the rope clip They will then inform the floor manager that the bar has been braked and rope clipped The floor manager may now attach their load to the bar.
4. Once the floor manager has attached the load and checked all fixings and equipment is safe to fly, they can instruct the fly person on how many weights to load into he cradle. The fly person will then ask the loading team on the loading gallery to apply that many weights to the cradle and they will confirm the number of weights and which cradle they will be adding them to.
5. Once the cradle is loaded the loading team will tell the fly person that the task has been completed, which cradle was loaded and how many weights was applied to that cradle.
7. The fly person can then tell the floor manager that the bar is loaded and that the load is ready to fly. Once the floor manger is happy that the piece can go out, he will ask the fly person to do so.
8. The fly person can then remove the rope clip release the brake slowly holding onto both ropes of that line as he does so to check if the load is in balance. If the load is not in balance he will instruct the loading team to adjust the weight by what is required, repeating the above steps in communication.
9. When the load is in balance, the fly person will tell the floor manager that the load is going out and when it is safe to do so, will fly it to the required height.
Note: Weights should never be directly transferred between cradles as this can result in loads being incorrectly or prematurely applied.
It is forbidden for anyone under the influence of drugs, alcohol or reaction impairing medication to engage in work activities.

## CPU006 Unloading CW Bars RA
Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITIES/TASKS
Task/Activity/Area: | Persons At Risk: | Ref: CPU006 | Initial Assessment Date: 01/06/16
Unloading Counterweight Bars | Employees/Students
Department: Production | Risk Assessment WITHOUT Controls: HIGH | Risk Assessment WITH Controls: LOW | Last Assessment Date: 23/5/18
Site/Location: New Athenaeum Theatre | Assessor: M. Stephen |  | Reviewed By: Steve MacLuskie
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C)
Manual handling - Fly weights | Bruises, strains, sprains and fractures | 3 x 3 (9) | All people handling fly weight will have undergone RCS Manual Handling Awareness training and cradle loading and unloading training. Cradles will be loaded by teams of two people wherever possible. Counterweights are loaded one at a time. Safety footwear EN ISO 20345 will be worn at all times. | 1 x 3 (3)
Manual handling - Removing scenery or lighting/sound equipment from counterweight bar. | Bruises, strains, sprains and fractures | 3 x 4 (12) | All participating people must have attended RCS Manual Handling awareness training. The weight of all items should be known prior to moving them. An appropriate amount of people used to maneouvre the item into position. Route of travel must be clear of all trip hazards. Clear communication must be maintained. Safety footwear EN ISO 20345 will be worn at all times. | 1 x 4 (4)
People being stuck by flying bars or flown scenery. | Injury from ranging from bruises to severe concussions/fractures. | 4 x 4 (16) | Stage access limited to only those working there at the time. Everyone made aware of bars in motion with clear vocalisation. Bars are watched in by an appointed person who is in clear communication with the fly person. Orange flashing light to be switched on when flying outside of technical rehearsals and performance in accordance with CPU 001 'Overhead Work' RA/SSoW and Safety Helmets EN 397 and Safety Footwear EN ISO 20345 must then be worn. Clearly marked deads will be applied to each bar that is in use to avoid overflying. Clear communication maintained between fly person and floor manager during flying. | 1 x 4 (4)
Falling fly weights from grid to stage level. | Injury ranging from bruises to severe concussions/fractures and death | 3 x 5 (15) | All people handling fly weights will have undergone RCS cradle loading and unloading training and be aware of the risks involved. While cradles are being loaded the area near the fly cages will be kept as free of people as possible by the floor manager. All 1/2 weights will be put in under a full fly weight to prevent half weight bouncing out of the cradle. Everyone at floor level will wear Safety Helmets - EN397 and Safety Footwear - EN ISO 20345 | 1 x 5 (5)
Runaway bars from incorrect sequence of unloading. | Injury ranging from bruises to severe concussions/fractures and death | 3 x 5 (15) | Load is removed from the bar before the cradle. Weights only removed from the cradle when it is safe to do so. Everyone at floor level will wear Safety Helmets - EN397 and Safety Footwear - EN ISO 20345 | 1 x 5 (5)
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:

## SSoW Counterweight Unloading
RCS Production Safe Systems of Work
Unloading Counterweight Bars
Hazards | PPE Required
Being struck by flying bars or scenery | Safety Helmet - EN 397
Falling weights from loading gallery | Safety Footwear - EN ISO 20345
Incorrect manual handling of weights or loads | Gloves (Optional - for comfort of fly person)
Runaway bars | Rope Lock
Manual Handling
Operational Procedure
An approved member of staff must be present in the venue
Personnel must include: Floor manager, fly person on fly floor, 2 persons on loading gallery.
1. The orange flashing light to denote 'overhead work' must be switched on. All ground personnel must then wear hard hats.
2. Floor manager will instruct the fly person to bring in the required bar when it is safe to do so and the fly person will fly it until it is fully in and so the cradle is against the buffers at the top of the system. Some unloading of weights at the fly floor and intermediate gallery may be required.
3. When the bar is fully in, the fly person will apply the brake and the rope clip. They will then inform the floor manager that the bar has been braked and clipped and instruct the loading team to remove all the weight from the cradle. The loading team will confirm the cradle number and instruction with the fly person.
4. When the cradle is empty the loading team will inform the fly person that the cradle has been unloaded, confirming its number once again. The fly person will then inform the floor manager that the cradle bar has be reweighted and the floor manager will then begin to remove the load from the bar.
5. Once the load has been removed from the bar the floor manager can inform the fly person that the bar is clear and the fly person can then remove the brake and clip from the lines and take the bar to the grid.
6. The brake can be applied and the clip returned to it's storage point.
Note: Weights should never be directly transferred between cradles as this can result in loads being incorrectly or prematurely applied.
It is forbidden for anyone under the influence of drugs, alcohol or reaction impairing medication to engage in work activities.

## CPU009 Manual Handling RA
Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITIES/TASKS
Task/Activity/Area: | Persons At Risk: | Ref: CPU 009 | Initial Assessment Date:
Manual Handling | Employees/Students/Public
Department: Production | Risk Assessment WITHOUT Controls: HIGH | Risk Assessment WITH Controls: LOW | Last Assessment Date: 24/5/18
Site/Location: Anywhere in RCS or anywhere on RCS duty. | Assessor: M. Stephen |  | Reviewed By: Steve MacLuskie
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C)
Manual Handling | Bruises, strains, sprains and fractures | 3 x 4 (12) | Avoid lifting if possible. Use mechanical or wheeled aids wherever possible. All people involved in activity will have undergone RCS Manual Handling Awareness training. All manual handling tasks assessed before they are undertaken. Assessment can be verbal. An adequate number of people will be allocated to each manual handling task. Safety footwear conforming to EN ISO 20345 will be worn at all times. Sturdy gloves can be worn for comfort. Weights should be clearly marked on all scenic elements. | 1 x 4 (4)
Slips, Trips, Falls | Injury ranging from bruises to broken bones | 2 x 4 (8) | Work area's will be kept as clear of as much unnecessary material as possible. Path will be cleared before attempting any manual handling tasks. Spotters will be deployed if necessary to clear way and spot hazards. Adequate lighting will be employed for each task. | 1 x 4 (4)
People being hit by moving scenery or equipment | Injuries ranging from bruising to broken bones | 2 x 4 (8) | Barriers and cones will be erected to section off the loading area preventing anyone not involved in the work entering the area. Spotters can be employed to keep the way clear. | 1 x 4 (4)
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:

## CPU011 Working at Height RA
RCS Risk Assessment Form
ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITIES/TASKS
Tutor/Lecturer/Production Manager - Comments
Task/Activity/Area: | Persons At Risk: | Reference: | Initial Assessment Date:
Working at Height | Employees/Visitors/Contractor/ Public/Students | CPU 010 | 2018-11-21
Department: | Risk Assessment WITHOUT Controls: | Risk Assessment WITH Controls: | Last Assessment Date:
Production | HIGH | LOW
Site/Location: | Assessor: Malcolm Stephen |  | Reviewed By: Steve MacLuskie
All RCS venues and working spaces | Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures Ri (L x C) | Control Measures | With Control Measures Ri (L x C)
Tutor/Lecturer/Production Manager - Comments
Overhead Work | Injury ranging from bruises to severe concussions/fractures/death. | 3 x 5 (15) | All task to be completed under CPU001 Overhead Work. | 1 x 5 (5)
Working on access equipment | Injury ranging from bruises to severe concussions/fractures/death. | 3 x 5 (15) | All task to be completed under CPU100 Tallescope Use or CPU103 Ladder Use Risk Assessments and Safe Systems of Work. All personnel using access equipment to have undergone relevant RCS training in the equipment being used. | 1 x 5 (5)
Working near/at and exposed edge (Restraint) | Injury ranging from bruises to severe concussions/fractures/death. | 3 x 5 (15) | All task to be completed under CPU001 Overhead Work. All participants to have undergone RCS Working at Height training. Personnel working near or at the exposed edge will wear harnesses conforming to EN361 or EN813 and be tethered to a known strong point. All equipment must be suitable for the task, have undergone an annual safety inspection, pre-use check, and be marked, labelled and checked in accordance with EN365. Tasks must only be attempted by staff or under the close supervision of Working at Height trained staff. | 1 x 5 (5)
Working over an exposed edge where there is a risk of a fall. (Arrest) | Injury ranging from bruises to severe concussions/fractures/death. | 3 x 5 (15) | All task to be completed under CPU001 Overhead Work. All participants to have undergone RCS Working at Height training. Personnel working over the exposed edge will wear harnesses conforming to EN361 or EN813 and be attached to a fall arrest device EN360 before approaching the hazard. All equipment must be suitable for the task, have undergone an annual safety inspection, pre-use check, and be marked, labelled and checked in accordance with EN365. Tasks must only be attempted by trained staff or with Working at Height trained staff supervision. | 1 x 5 (5)
Working at height using rope access | Injury ranging from bruises to severe concussions/fractures/death. | 3 x 5 (15) | All task to be completed under CPU001 Overhead Work. All participants to have undergone RCS Working at Height training. All equipment must be suitable for the task, have undergone an annual safety inspection, pre-use check, and be marked, labelled and checked in accordance with EN365. Tasks must only be performed by qualified IRATA personnel. All work must be supervised by an IRATA qualified staff member who is also on site to rescue the operator if required. A rescue plan must be in place before each operation commences. | 1 x 5 (5)
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:

## RA Tallescope Use and Movement
Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITES/TASKS
Task/Activity/Area: | Persons At Risk: | Ref: CPU100 | Initial Assessment Date: 28/09/17
Use of Tallescope | Employees/Visitors/Contractors/Students
Department: Production | Risk Assessment WITHOUT Controls: VERY HIGH | Risk Assessment WITH Controls: MEDIUM | Last Assessment Date:
Site/Location: All RCS venues in which Tallescope can be deployed | Assessor: Dave Evans |  | Reviewed By:
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C)
Fall of user in cage because of Tallescope overturning | Death or serious injury to cage user and ground based operators | 4 x 5 | Supervision, assess and monitor floor surfaces and working conditions (especially good light and low noise levels) Operated by trained users only in guidelines with the SSoW | 2 x 5
Collapse of Tallescope | Death, serious injury to cage user and ground based operators | 4 x 5 | Maintenance - annually by certified personnel Training - provision of suitable training in accordance with manufacturers guidelines | 2 x 5
Head injury (at height) | Minor head injury (Tallescope would move at 1mph so likelihood of high impact head injury minimal) | 3 x 3 | Hard hat (with chin strap) rule or bump camp in accordance with ABTT \ SSoW user guidelines | 1 x 1
Head injury (floor level) | Death, serious injury to ground based operators and those in the vicinity of base of Tallescope | 4 x 5 | Adherence to RCS work at height RA and SSoW | 2 x 1
Fatigue: climbing and in/out of cage | Death, serious injury to cage user and ground based operators | 3 x 5 | Adherence to Safe system of work and training in Tallescope Use Rotate technicians if possible Occupied Tallescope moved slowly, short moves, 4 x outriggers on | 2 x 5
Falling objects | Death, serious injury to ground based operators or those in vicinity of base of Tallescope | 4 x 5 | Eliminate, secure or contain objects used at height Implementation of exclusion zone at base of Tallescope when work being carried out | 3 x 1
Moving in low light environments | Serious injury to ground based operators or causing one of above hazards | 4 x 5 | If & when Tallescope is required to move, an on site movement plan is discussed, checked and managed by the Tallescope users BEFORE movement occurs. If required personal secondary illumination or venue illumination to be used before movement occurs. | 2 x 1
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:
Take Ownership - Be Accountable - Get Involved - Communicate - Collaborate
I confirm that the significant findings of the assessments in this file have been communicated to me and the control measures explained. I understand the legal requirements for me to comply with the control measures and to co-operate with my employer in the interest of health and safety. I agree to abide with the controls in place and to report any defects or problems with the systems.
Employee Name |  | Employee Signature |  | Date

## SSoW Tallescope Use
RCS Production Safe Systems of Work
Use of Tallescope whilst static
Hazards
Falling objects. Incorrect Manual Handling. Toppling of Tallescope. Working in low light
Required equipment
Hard hats, protective footwear, secondary illumination
Operational Procedure
This Operation Should Only Be Carried Out By Trained, Competent People
Pre Use Considerations:
1. Planning Establish a safe system of work appropriate to the task, the premises and the staff available. Confirm that a Tallescope is the most appropriate equipment for the task. Ensure that everyone using a Tallescope has been properly instructed in its use. Documented training is recommended for all users and supervisors. Employers should confirm that the personnel concerned are fit for working at height. There should be a reliable means of communication available to summon emergency services at all times that people are working at height.
2. Lone working Working alone at height or with access equipment should not be allowed. A minimum of three people is recommended when using a Tallescope.
3. Illumination levels It is important to ensure there is sufficient light where work at height is to be carried out. Adequate lighting is necessary for safely erecting and positioning a Tallescope. There should be good light to ensure all changes in level are easily seen as well as hazards such as steps or stage edges. Blackouts or low light levels are potential hazards. A sudden increase in light level can also create sudden difficulty in vision and this should be avoided. Even with warning, changes in light levels can adversely affect sight and balance, so a system of work that allows a level of light appropriate for the work in hand is important. When focusing luminaires, the policy of cross fading between the luminaire to be focused and a working light state is good practice and should be included in induction training for lighting operators.
4. Noise levels Similar precautions are needed concerning sound levels. High sound levels will inhibit clear communication, which is essential when work at height is in progress. Loud noise can cause accidents. All technicians involved in working at height operations should be able to hear clearly.
5. Floors Check that the floor and the supporting surface are strong enough to support the combined weight of the Tallescope and the user. The floor must be sufficiently rigid to assure that flexible surfaces will not affect the stability of the Tallescope. In particular avoid placing the wheels of the Tallescope on dip traps.
6. Front edge of stage Particular attention should be paid to unsecured edges of the stage, especially during fit up when "edge battens" may not have been fitted yet.
7. PPE All those close-by should wear hard hats (BS EN 397: Industrial safety helmets for ‘stage work’) if there is any risk of falling objects. The technician in the cage should wear a bump cap (BS EN 812: Industrial bump caps) or a helmet with a chin strap (BS EN 12492: Helmets for mountaineers safety requirements) if there are any obstructions overhead. Consider what other PPE such as safety footwear should be provided if any. However do not wear loose fitting gloves or heavy boots when climbing.
USE
1) Never adjust level, set brakes or move outriggers whilst someone is on the ladder. 2) Never attempt to lift or level the base, raise the cage or remove the outriggers unless the Tallescope is unoccupied. 3) Do the work only from the cage (not from the ladder) and ensure the swing guardrail is securely closed. Do not gain extra height by standing on guardrails, toe-boards or by putting ladders or boxes on the cage floor. 4) Consider the available headroom when extending the ladder. Users should be able to stand comfortably on the cage floor. Do not put loose tools where they could fall and cause an injury. 5) Use the storage bag (if fitted) for materials and secure tools with lanyards. 6) Do not lean out sideways from the cage to lift even small, light items such as colour frames. 7) A hoist “chain bag” on a hand rope is an excellent method of transferring materials and small items up and down a Tallescope. 8) Use a separate rope-and-pulley operated from the floor or suitable position to lift and lower heavy equipment where necessary - a guideline would be 5kg. 9) Do not rig a pulley to the Tallescope. Maximum platform load 115kg (1 person). This could easily be exceeding by 1 person and one heavy lantern\piece of equipment. 10) Fatigue is a hazard which may be partly controlled by using more than one technician to work at height and by planning the route for the Tallescope to require as few climbs and descents wherever possible. Rotating technicians is usually only practical if their competence is consistent.
It is essential to carry out a pre-use check before you climb the Tallescope ladder. Ensure: - floor structure supporting the Tallescope and outriggers is strong and stable - Tallescope is visually sighted vertical (and confirmed with the bull’s eye spirit level) - Tallescope is not too close to a change in floor level - Tallescope is positioned close enough to reach the work - diagonal braces on trunnion frame are located and snapped on - all four leg extension locking mechanisms are secure - all four push-pull posts are fixed in place on corners of the trunnion frames - all four outriggers are fully extended, two on each long side, and clips set securely - both mast hooks are fully engaged - both mast braces are locked - both ladder hooks are fully engaged - all four brakes are locked Use the power in your legs as much as possible when climbing up or down the ladder, avoid pulling yourself up. Do not 'hug' the ladder; stand out so you can see where you are putting your feet. Use a slow, steady pace when climbing up or down, one rung at a time. Grasp the rungs and look out for any sharp edges that might cut your hands.
It is forbidden for anyone under the influence of drugs, alcohol or reaction impairing medication to engage in work activities anywhere on Stage level, Grid or Fly Floors.

## SSoW Tallescope Movement
RCS Production Safe Systems of Work
Use of Tallescope and Its movement whilst occupied
Hazards
Falling objects. Incorrect Manual Handling. Toppling of Tallescope. Working in low light
Required equipment
Hard hats, protective footwear, secondary illumination
Operational Procedure
This Operation Should Only Be Carried Out By Trained, Competent People
1. A logbook shall be kept for each Tallescope.
2. At least one technician working on the job shall have been trained in the SSOW for Moving Tallescopes.
3. A visual inspection shall be made before each use of the Tallescope. If there be any fault the Tallescope shall be taken out of service immediately, labelled as Not to be used, and the defect noted in the logbook.
4. The Tallescope shall be erected in accordance with the manufacturer’s instructions. If only two outriggers are deployed, the Tallescope must not be moved with a person in the cage.
5. If it is intended to move a Tallescope with a person in the cage four stabilizers shall be deployed at all times
a) at least two technicians who have RCS training will be present
b) there shall be a supervisor who is not moving the Tallescope
c) there shall be no obstructions along the route of the movement at stage level or overhead. If these are present a movement plan should be pre discussed and agreed by all four members of the team involved in moving the Tallescope.
d) the stabilizers must be locked off just above the floor (not more than 10mm above the floor)
e) the Tallescope must only be moved along its longest axis
f) movement of the Tallescope shall be by pushing and pulling on the extended uprights on the base frames (trunnions) and NOT the diagonals
g) the Tallescope shall only be moved slowly and smoothly (not more than 0.5m per second/1mph)
h) the Tallescope must be moved by at least two people, the technician pushing the Tallescope must confirm there are no floor level hazards and also guide the direction of the Tallescope. The technician pulling the Tallescope will confirm if there are overhead hazards in conjunction with the basket user.
i) the technician in the cage must maintain a firm hand hold whilst the Tallescope is being moved
j) the technician in the cage shall instruct the technicians moving the Tallescope and the instructions acknowledged before movement occurs
k) the castor brakes shall be applied before any work other than light work begins (light work is such as focusing luminaires, any work involving exertion or lateral pressure is no light work)
l) the details of each job and the personnel must be recorded in the log book and be signed off by the trained person present.
It is also important to note that before a Tallescope is used there must be a rescue plan in place in order to cope with the retrieval of an operative who becomes incapacitated within the cage. In summary the key points for moving an occupied Tallescope are:
a) the stage is horizontal and level
i. the Tallescope is the 2011 (or later) year of manufacture model or ii. the Tallescope has been fitted with a manufacturer’s upgrade kit comprising two additional outriggers (four in total), for 450mm push-pull posts and for non-lift brake castors; addition strengthening may also be required.
b) A minimum of four personnel are available to carry out operations: one in the cage, one supervisor and two moving the Tallescope. Where possible, if the duration of Tallescope use extends beyond 45 minutes, the cage user is rotated for another user to prevent fatigue.
It is forbidden for anyone under the influence of drugs, alcohol or reaction impairing medication to engage in work activities anywhere on Stage level, Grid or Fly Floors.

## RA - Lighting Work - NAT
Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITES/TASKS
Task/Activity/Area: | Persons At Risk: | Ref: CPU101 | Initial Assessment Date:
Lighting Rigging, Focussing, Plotting | Employees/Visitors/Contractor/ Students
Department: Production | Risk Assessment WITHOUT Controls: VERY HIGH | Risk Assessment WITH Controls: LOW | Last Assessment Date:
Site/Location: New Athenaeum Theatre | Assessor: Dave Evans |  | Reviewed By:
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C)
Slips Trips and Falls | Sprains, broken bones | 4 x 3 | Venue will be kept clear and tidy during fit up. Liquids prohibited in venue unless in sealed container, and then only water. Floor area will be kept clear during fit up. Catwalks above the auditorium area to cleared as continual process during rigging and checked before focus occurs | 2 x 3
Fixture falling into auditorium | Death, serious injury | 4 x 5 | Ensure all crew members are trained in rigging fixtures. Lanterns and where appropriate their accessories MUST make use of a certified secondary fixing bond and this must be implemented as per user training. Ensure fixture is securely rigged following SSoW Ensure that area below work is kept clear of all personnel. Use of orange hazard warning beacon when overhead work is carried out When hoisting lanterns into elevated areas using a rope and pulley system the load being hauled must be suitable and not exceed manual handling expectations. When removing lanterns or equipment from the hauling apparatus, they MUST have either been attached by a suitable fixing mechanism to the building structure or be laid on the floor\work platform BEFORE the hauling apparatus has been removed. | 1 x 5
Electrocution \ Electric shock | Death, serious injury | 2 x 5 | All fixtures will have passed a PAT Test in the last 12 months and carry suitable markings as proof. All fixtures will undergo a visual inspection for faults before use. Faults are to be reported to the relevant persons. All electrical outlets are protected under approved IEE protection devices (RCD, MCB, RCBO) | 2 x 5
Tools falling from Tallescope or catwalks | Death, serious injury | 4 x 5 | All tools will be secured to personnel using a suitable lanyard All crew below Tallescope and catwalks will be wearing hard hats at all times including during focus No unauthorised persons will be allowed in the venue during the session When hard hats are not appropriate for people in the auditorium, they will be moved away from the over head work area and this exclusion zone will be managed by a member of crew on the ground. | 1 x 5
Burns from hot metalwork on lanterns | Burns | 4 x 2 | Persons required to focus are trained in the safe manipulation of units if they have been illuminated for long periods of time and have become hot. Where practicable, lanterns should be off or at a very low dimmed level to prevent heat built up. | 2 x 2
Working in low light leading to slips trips and falls | Sprains, broken bones | 4 x 3 | As above regarding "slips trips and falls" Additional: Use of supplementary personal illumination where required Use of venue working light when required A verbal call and if possible visual representation (working light flashed) BEFORE stage is darkened. N.B. When working with hearing impaired practitioners, a verbal, visual and if possible British Sign Language indication should be provided and acknowledged before working light is dropped. If set and other mitigating factors increase the risk of injury to hearing impaired practioners during their time on stage a specific risk assessment should be carried out. | 2 x 2
Injury from use of hand tools | Minor cuts and bruises | 3x2 | Whilst care must be taken when using hand tools some minor injuries may occur due to the physical nature of the work. It may be appropriate to wear suitable gloves to protect hands but not inhibiting dexterity. Suitable training shall be provided to those needing to utilise hand tools in to minimise risk as much as possible. | 2x2
Injury from working at height in auditorium | Sprains, broken bones, death | 3 x 5 | When working to rig lanterns\equipment in the auditorium balcony edges, technicians are required to wear a fall restraint harness and make use of a fall restraint lanyard. The user can rig safely by being restrained from falling over the balcony edge, due to the nature of the lanyard, thusly a fall with serious injury or death has been limited in likelihood. When working on catwalks above the auditorium technicians should follow the SSoW to prevent a fall from height. | 2x3
Use of Tallescope - Falls from height SEE SEPARATE RISK ASSESSMENT | SEE SEPARATE RISK ASSESSMENT | SEE SEPARATE RISK ASSESSMENT | SEE SEPARATE RISK ASSESSMENT | SEE SEPARATE RISK ASSESSMENT
Use of Ladders - Falls from height, SEE SEPARATE RISK ASSESSMENT | SEE SEPARATE RISK ASSESSMENT | SEE SEPARATE RISK ASSESSMENT | SEE SEPARATE RISK ASSESSMENT | SEE SEPARATE RISK ASSESSMENT
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:
Take Ownership - Be Accountable - Get Involved - Communicate - Collaborate
I confirm that the significant findings of the assessments in this file have been communicated to me and the control measures explained. I understand the legal requirements for me to comply with the control measures and to co-operate with my employer in the interest of health and safety. I agree to abide with the controls in place and to report any defects or problems with the systems.
Employee Name |  | Employee Signature |  | Date

## SSOW Rigging Lanterns NAT
RCS Production Safe Systems of Work
Rigging of Lanterns- New Athenaeum Theatre
Hazards
Falling objects. Incorrect Manual Handling. Working in low light
Required equipment
Hard hats, protective footwear, secondary illumination
Operational Procedure
This Operation Should Only Be Carried Out By Trained, Competent People
Pre Task Considerations:
1. Planning Establish a safe system of work appropriate to the task, the premises and the staff available.
2. Lone working Working alone at height or with access equipment should not be allowed.
3. Illumination levels It is important to ensure there is sufficient light where work at height is to be carried out. Normal stage working light may not be sufficient. Adequate lighting is necessary for safely working. There should be good light to ensure all changes in level are easily seen as well as hazards such as steps or stage edges. Blackouts or low light levels are potential hazards. A sudden increase in light level can also create sudden difficulty in vision and this should be avoided. Even with warning, changes in light levels can adversely affect sight and balance, so a system of work that allows a level of light appropriate for the work in hand is important. Where appropriate secondary or supplemental personal illumination can be used.
4. Noise levels Similar precautions are needed concerning sound levels. High sound levels will inhibit clear communication, which is essential when work at height is in progress. Loud noise can cause accidents. All technicians involved in working at height operations should be able to hear clearly. Work in noisy environments should be managed so that good communication can still be achieved if high noise levels are unavoidable.
5. Access Equipment Ensure that all access equipment to be used is suitable for the task at hand. Refer to the corresponding SSoW for the access equipment to be used.
6. Electrical hazards Proximity to electrical hazards must be considered. Ensure that serious electrical hazards such as exposed terminals or damaged plug tops either do not exist or are made safe before the work begins. Equipment operating at high voltages such as neon tubes requires extra precautions.
5. PPE All those close-by overhead work should wear hard hats (BS EN 397: Industrial safety helmets for ‘stage work’ or BS EN 12492: "Helmets for mountaineers" where the venting system can be closed or suitably constructed as to prevent falling objects and lateral objects from penetrating into the helmet) if there is any risk of falling objects. Consider what other PPE such as safety footwear should be provided if any. However do not wear loose fitting gloves or heavy boots when climbing access equipment.
Considerations When Carrying Out the Task
1) Before a lantern is to be rigged, it should be fully checked for the following: - Damage to any structural part of the lantern and damage to its rigging equipment (hook clamp, bolt assembly for hook clamp, safety bond) - Damage to any electrical apparatus associated with the lantern (plug, cable tail, outlet socket where applicable) - Presence of all fixtures and fittings associated with safe use of unit (Fresnels require a lens mesh, S4 PARS require a lens mesh, profiles must have retaining bolts on gates and lens tubes etc) - Bolt assembly on hook clamp must be as follows - hex bolt, washer, hook clamp, washer, yolk\arm, washer, split locking washer, retaining nut\wing nut - refer to diagram in Athenaeum Technical Stores for visual graphic. 2) a) When rigging lanterns on a counterweight bar ENSURE you have liaised with appropriate TSM management before adding weight to a bar. Hang unit by its appropriate clamp, and IMMEDIATELY apply the safety bond to avoid it being forgotten. Tighten restraining bolts (wing bolts) to ensure the unit cannot become detached from the flying bar. b) When rigging a lantern in the front of house areas in the Athenaeum using unit track system, a user will wear a fall restraint harness as provided by the venues office. This harness is used in conjuction with a restraining lanyard attached to EITHER, a wall anchor point (eye bolt fixed into wall) or the hand rail BEHIND the 2nd row of seating if in the center section of the balcony. When using the handrail point, an additional (purple and black) strop is choke hitched around the handrail, and the fall restraint lanyard is karabinered to this. A unit will have its safety bond attached to a seperately mounted eye bolt fixing within the unitrack. Two units may share one eyebolt fixing and the safety should made made taught where possible to prevent a drop or swing if the lantern were to fail in its primary fixing. c)When rigging a lantern on the catwalks or the gods rails above the auditorium, a unit should be rigged by lifting the unit with both hands and hooking it to the appropriate lighting bar. If the unit is bulky, or the user feels more confident in the following, then BEFORE the unit is lifted into position the safety bond MUST be attached to the lighting rigging rail before lifting the unit into a void space above the auditorium. Where the safety bond attached to the unit does not extend enough to allow pre attachment, a longer safety bond or steel drift and Karabiners should be used. A good method would be to lay the unit on the catwalk floor or gods floor, attach the safety bond and then begin manipulating the lantern into position. 3) If access equipment is required for rigging REFER TO CORRESPONDING SSoW for said piece of access equipment 4) When lifting lanterns to and from ladders or Tallescope, a suitable rigging rope and pulley should be used in accordance with RCS training. Lanterns and equipment are to be hauled into position by a separate team. DO NOT climb a ladder carrying lanterns and similarly do not haul lanterns into the rig from the top of the Tallescope. Use a separate rope and pulley operated by persons either on the floor or in a position to assist.
It is forbidden for anyone under the influence of drugs, alcohol or reaction impairing medication to engage in work activities anywhere on Stage level, Grid or Fly Floors.

## RA Lighting Ladder Use
Risk Assessment Form ASSESSMENTS TO BE COMPLETED BEFORE STARTING NEW ACTIVITES/TASKS
Task/Activity/Area: | Persons At Risk: | Ref: CPU103 | Initial Assessment Date: 02/10/17
Ladders use | Employees/Contractor/Students
Department: Production | Risk Assessment WITHOUT Controls: VERY HIGH | Risk Assessment WITH Controls: MEDIUM | Last Assessment Date:
Site/Location: RCS General | Assessor: Dave Evans |  | Reviewed By:
| Signature: |  | Signature:
Hazard Something with the potential to cause harm | Consequence The effect of that harm | Without Control Measures | Control Measures | With Control Measures
|  | Ri (L x C) |  | Ri (L x C)
Fall from ladder - used in "lean" position | Death | 3 x 5 | All persons using a ladder will follow the strict guideline in the RCS Ladder Training and Ladder SSoW which by proxy mimics the HSE Safe use of Ladders INDG455 (publish 1/14) No work on ladders should be undertaken unless these guidelines are followed A copy of these guidelines can be found below or presented to anyone who has not undergone RCS training or as a refresher to the working practices. | 2 x 5
Fall from ladder - used in "A frame" or Stepladder position | Death | 3 x 5 | All persons using a ladder will follow the strict guideline in the RCS Ladder Training and Ladder SSoW which by proxy mimics the HSE Safe use of Ladders INDG455 (publish 1/14) No work on ladders should be undertaken unless these guideline are followed A copy of these guidelines can be found below presented to anyone who has not undergone RCS training or as a refresher to the working practices. | 2 x 5
Equipment falling whilst using ladder for work | Head/physical injury to those working below | 3 x 5 | Persons working below ladder shall wear suitable head protection to BS EN397 or EN12492 Where possible tools and other items should be attached to the user or the building fabric using a suitable lanyard\fall prevention mechanism | 2 x 4
Dropping equipment whilst climbing ladder | Head/physical injury to those working below | 3 x 5 | As per RCS ladder use guideline, no equipment is to be carried up the ladder by a user. Equipment must be hauled into position using a rope and pulley system by other parties. | 2 x 4
This risk assessment must be used in conjunction with further guidelines and SSoW.
FURTHER ACTIONS/MEASURES REQUIRED |  | Target Date: | Responsible Person: | Completion Date:
Continual checking of HSE guidelines on ladder use for compliance with guidelines |  | 2017-01-15 | Dave Evans
Take Ownership - Be Accountable - Get Involved - Communicate - Collaborate
I confirm that the significant findings of the assessments in this file have been communicated to me and the control measures explained. I understand the legal requirements for me to comply with the control measures and to co-operate with my employer in the interest of health and safety. I agree to abide with the controls in place and to report any defects or problems with the systems.
Employee Name |  | Employee Signature |  | Date
Royal Conservatoire of Scotland
Ladder Use
Ladder condition
ü CHECK THE STILES - Is the ladder straight – i.e. no visible sign of bowing or warping?
ü CHECK THE RUNGS - Are the rungs in good condition – i.e. no deformation or damage?
ü CHECK THE FEET - Does the bottom of the ladder have suitable footing – i.e. rubber/plastic feet – that allows it to be even when in use?
ü CHECK THE LOCKING MECHANISMS – Most ladders will have some form of locking mechanism to ensure the stiles do not close shut or over open when in use (physical metal locking bar or webbing tape or locking top platform). Are these in suitable undamaged condition?
ü Are any other accessories in good condition? Platform on painting type ladders or step ladder, top hand rail on low step ladders etc.
Ladder use – before climbing
ü Is the ladder long enough and positioned to reach the work safely?
ü Is the ladder sited on stable and even ground? If not are proprietary stabilising tools available?
ü Are ladders secured so they cannot slip, usually by being tied at the top and/or footed at the base?
ü Is the ladder angled to minimise the risk of slipping outwards? As a rule of thumb, the angle should be one distance out for every four up?
ü If being used for access, does the ladder extend about 1 m above the working platform to provide a handhold for people getting on and off?
ü Is the ladder designed to take the loads put on it?
ü Are materials stored so the load is spread evenly?
Ladder use – Whilst in use – Leaning Ladders
ü only carry light materials and tools – read the manufacturers’ labels on the ladder and assess the risks;
ü don’t overreach – make sure your belt buckle (navel) stays within the stiles; always grip the ladder and face the ladder rungs while climbing or
ü descending – don’t slide down the stiles;
ü On a leaning ladder, don’t work off the top three rungs, and try to make sure the ladder extends at least 1 m (three rungs) above where you are working;
avoid holding items when climbing (consider using a tool belt);
ü maintain three points of contact when climbing (this means a hand and two feet) and wherever possible at the work position
ü where you cannot maintain a handhold, other than for a brief period (e.g. to hold a nail to knock it in, starting a screw etc.), you will need to take other measures to prevent a fall or reduce the consequences if one happened;
 Never carry any equipment up the ladder. All equipment should be hoisted into position using a rope and pulley setup by persons either below or by persons in a suitable position to allow equipment to be positioned for attachment to rigging points.
Ladder use – Whilst In Use - Stepladders
ü only carry light materials and tools;
ü don’t overreach;
ü don’t stand and work on the top three steps (including a step forming the very top of the stepladder) unless there is a suitable handhold or the manufacturers guidelines\manual\pictogram indicate the correct way to do this;
ü ensure any locking devices are engaged;
ü try to position the stepladder to face the work activity and not side on.
However, there are occasions when a risk assessment may show it is safer to work side on, e.g. between set items when you can’t engage the stepladder locks to work face on because of space restraints in narrow aisles, but you can fully lock it to work side on;
ü try to avoid work that imposes a side loading, such as side-on drilling through solid materials (e.g. bricks or concrete); where side-on loadings cannot be avoided, you should prevent the steps from tipping over, e.g. by tying the steps. Otherwise, use a more suitable type of access equipment;
ü maintain three points of contact at the working position. This means two feet and one hand, OR when both hands need to be free for a brief period, two feet and the body supported by the stepladder. Zargee ladders have been designed as means of work at height for short duration utilising stepladder working practices. Therefore if the body is supported by the rungs and stiles of the ladder, short duration hands free work is acceptable. Within the CST when working on the seating bank, the "Little Giant Ladders" may be used in its special function of one side leaning as close to vertical against the wall, and one side extended onto the second highest row of seats, making a locked, safe a frame step ladder. This allows for safe front working on a step ladder.
When is a ladder the most suitable equipment?
The law says that ladders can be used for work at height when a risk assessment has shown that using equipment offering a higher level of fall protection is not justified because of the low risk and short duration of use; or there are existing workplace features which cannot be altered. Short duration is not the deciding factor in establishing whether use of a ladder is acceptable or not – you should have first considered the risk. As a guide, if your task would require staying up a leaning ladder or stepladder for more than 30 minutes at a time, it is recommended that you consider alternative equipment. You should only use ladders in situations where they can be used safely, e.g. where the ladder will be level and stable, and where it is reasonably practicable to do so, the ladder can be secured.
When deciding if it is safe to carry out a particular task on a stepladder where you cannot maintain a handhold (e.g. to put a box on a shelf, screw into a flat, rig on a bar), this needs to be justified, taking into account: - the height of the task; - whether a handhold is still available to steady yourself before and after the task; - whether it is light work; - whether it avoids side loading; - whether it avoids overreaching; - whether the stepladder can be tied if necessary (e.g. when side-on working).
This diagram indicates that using two feet, as well as upper legs by leaning into the step ladder, three points of contact can be maintained whilst the hands are not used for holding on to the ladder

## SSoW Lighting Ladder Use
RCS Production Safe Systems of Work
Ladders Use - Lighting
Hazards
Falling objects. Incorrect Manual Handling. Working in low light. Fall From Height
Required equipment
Hard hats, protective footwear, secondary illumination
Operational Procedure
This Operation Should Only Be Carried Out By Trained, Competent People
Pre Task Considerations:
1. Planning Establish a safe system of work appropriate to the task, the premises and the staff available.
2. Lone working Working alone at height or with access equipment should not be allowed.
3. Illumination levels It is important to ensure there is sufficient light where work at height is to be carried out. Normal stage working light may not be sufficient. Adequate lighting is necessary for safely working. There should be good light to ensure all changes in level are easily seen as well as hazards such as steps or stage edges. Blackouts or low light levels are potential hazards. A sudden increase in light level can also create sudden difficulty in vision and this should be avoided. Even with warning, changes in light levels can adversely affect sight and balance, so a system of work that allows a level of light appropriate for the work in hand is important. Where appropriate secondary or supplemental personal illumination can be used.
4. Noise levels Similar precautions are needed concerning sound levels. High sound levels will inhibit clear communication, which is essential when work at height is in progress. Loud noise can cause accidents. All technicians involved in working at height operations should be able to hear clearly. Work in noisy environments should be managed so that good communication can still be achieved if high noise levels are unavoidable.
5. Access Equipment Ensure that all access equipment to be used is suitable for the task at hand. Refer to the corresponding SSoW for the access equipment to be used.
6. PPE All those close-by overhead work should wear hard hats (BS EN 397: Industrial safety helmets for ‘stage work’ or BS EN 12492: "Helmets for mountaineers" where the venting system can be closed or suitably constructed as to prevent falling objects and lateral objects from penetrating into the helmet) if there is any risk of falling objects. Consider what other PPE such as safety footwear should be provided if any. However do not wear loose fitting gloves or heavy boots when climbing access equipment.
Considerations When Carrying Out the Task
Before using a ladder, it should be fully checked for the following: - CHECK THE STILES - Is the ladder straight – i.e. no visible sign of bowing or warping? - CHECK THE RUNGS - Are the rungs in good condition – i.e. no deformation or damage? - CHECK THE FEET - Does the bottom of the ladder have suitable footing – i.e. rubber/plastic feet – that allows it to be even when in use? - CHECK THE LOCKING MECHANISMS – Most ladders will have some form of locking mechanism to ensure the stiles do not close shut or over open when in use (physical metal locking bar or webbing tape or locking top platform). Are these in suitable undamaged condition? - Are any other accessories in good condition? Platform on painting type ladders or step ladder, top hand rail on low step ladders etc
Ladder use – before climbing: - Is the ladder long enough and positioned to reach the work safely? - Is the ladder sited on stable and even ground? If not are proprietary stabilising tools available? - Are ladders secured so they cannot slip, usually by being tied at the top and/or footed at the base? - Is the ladder angled to minimise the risk of slipping outwards? As a rule of thumb, the angle should be one distance out for every four up? - If being used for access, does the ladder extend about 1 m above the working platform to provide a handhold for people getting on and off? - Is the ladder designed to take the loads put on it? - Are materials stored so the load is spread evenly?
Ladder use – Whilst in use – Leaning Ladders - Only carry light materials and tools – read the manufacturers’ labels on the ladder and assess the risks; - Don’t overreach – make sure your belt buckle (navel) stays within the stiles; - Always grip the ladder and face the ladder rungs while climbing or descending – don’t slide down the stiles; - On a leaning ladder, don’t work off the top three rungs, and try to make sure the ladder extends at least 1 m (three rungs) above where you are working; - Avoid holding items when climbing (consider using a tool belt); - Maintain three points of contact when climbing (this means a hand and two feet) and wherever possible at the work position - Where you cannot maintain a handhold, other than for a brief period (e.g. to hold a nail to knock it in, starting a screw etc), you will need to take other measures to prevent a fall or reduce the consequences if one happened; - Never carry any equipment up the ladder. All equipment should be hoisted into position using a rope and pulley setup by persons either below or by persons in a suitable position to allow equipment to be positioned for attachment to rigging points.
Ladder use – Whilst In Use - Stepladders - Only carry light materials and tools; - Don’t overreach; - Don’t stand and work on the top three steps (including a step forming the very top of the stepladder) unless there is a suitable handhold or the manufacturers guidelines\manual\pictogram indicate the correct way to do this; - Ensure any locking devices are engaged; - Try to position the stepladder to face the work activity and not side on. - However, there are occasions when a risk assessment may show it is safer to work side on, e.g. between set items when you can’t engage the stepladder locks to work face on because of space restraints in narrow aisles, but you can fully lock it to work side on; - Try to avoid work that imposes a side loading, such as side-on drilling through solid materials (e.g. bricks or concrete); - Where side-on loadings cannot be avoided, you should prevent the steps from tipping over, e.g. by tying the steps. Otherwise, use a more suitable type of access equipment; - Maintain three points of contact at the working position. This means two feet and one hand, OR when both hands need to be free for a brief period, two feet and the body supported by the stepladder. Zargee type ladders have been designed as means of work at height for short duration utilising stepladder working practices. Therefore if the body is supported by the rungs and stiles of the ladder, short duration hands free work is acceptable. Within the CST when working on the seating bank, the "Little Giant Ladders may be used in its special function of one side leaning as close to vertical against the wall, and one side extended onto the second highest row of seats, making a locked, safe a frame step ladder. This allows for safe front working on a step ladder.
When deciding if it is safe to carry out a particular task on a stepladder where you cannot maintain a handhold (e.g. to put a box on a shelf, screw into a flat, rig on a bar), this needs to be justified, taking into account: - The height of the task; - Whether a handhold is still available to steady yourself before and after the task; - Whether it is light work; - Whether it avoids side loading; - Whether it avoids overreaching; - Whether the stepladder can be tied if necessary (e.g. when side-on working).
It is forbidden for anyone under the influence of drugs, alcohol or reaction impairing medication to engage in work activities anywhere on Stage level, Grid or Fly Floors.