**Inner Space 2021 (WT)**

Production Schedule

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Date | Time | Activity | Notes |
| Tues | 7/12/21 | 9:30 | Brief – Ath Stage |  |
|  |  | 9:45 | Rig Stage / LX / Sound | This will include marking up |
|  |  | 13:00 | Break |  |
|  |  | 14:00 | Cont Rig Stage / LX / Sound |  |
|  |  | 17:30 | End |  |
|  |  |  |  |  |
| Wed | 8/12/21 | 9:30 | Cont Rig Stage / LX / SoundFit Up of Deck |  |
|  |  | 12:00 | FocusSound Break |  |
|  |  | 13:00 | BreakSound Plot Session 1 |  |
|  |  | 14:00 | Cont Focus | If focus finishes early – skip to ‘Plot Session 1’ |
|  |  | 16:00 | Plot Session 1 |  |
|  |  | 17:30 | End |  |
|  |  |  |  |  |
| Thurs | 9/12/21 | 9:30 | Brief – Ath Stage |  |
|  |  | 9:45 | Plot Session 2  | If this is not needed, tech rehearsals may begin |
|  |  | 11:00 | Performer’s H+S WalkStage reset | Stage Management to be carrying out reset whilst walk is happening |
|  |  | 12:00 | Tech Rehearsal 1 |  |
|  |  | 13:00 | BreakSound Notes and Quiet Time |  |
|  |  | 14:00 | Tech NotesSound Break (1Hr) | Sound to break for one hour to allow for quiet time and notes at 13:00 |
|  |  | 14:30 | Implementation of NotesStage Reset | If notes are minimal, the tech rehearsal may be moved forward |
|  |  | 15:30 | Dress Rehearsal 1 |  |
|  |  | 16:30 | Final Notes |  |
|  |  | 17:00 | Break |  |
|  |  | 18:00 | Crew CallCrew BriefStage Reset |  |
|  |  | 18:50 | Performer Half Hour CallFoH ResetStage Checks |  |
|  |  | 19:15 | House Open |  |
|  |  | 19:30 | PERFORMANCE |  |
|  |  | 20:36 | END OF PERFMANCERemove all FoH ArticlesPile Up PropsTidy B/S Area Ready for Strike |  |
|  |  | 21:30 | End |  |
|  |  |  |  |  |
| Fri | 10/12/21 | 9:30 | Brief |  |
|  |  | 10:00 | Strike Sound / LX / Stage |  |
|  |  | 13:00 | Break |  |
|  |  | 14:00 | Cont Strike Sound / LX/ Stage | If this extra strike session is not required, we may skip to ‘Debrief’ and ‘End’ |
|  |  | 15:30 | De-Brief |  |
|  |  | 16:30 | End! |  |